## User stories
Overall description of the project
Temporary file sharing service that can be used without registration and is cleaned up after some time. Some files can be shared for a single download, with a password and with ability to preview the content.
Milestone | User story | Acceptance criteria | Out of scope | Technical acceptance criteria | Technical task details | Design | QA | PM | Запитання | Відповідь
Bootstraping | As a user, I want to be able to open a website that says that I can share the files | - open a link and see the plain text | - styling - custom domain - connection to backend | - frontend is deployed - this should be a production build (not development setup) - frontend is deployed by commiting to Git (not manually) | - get in touch with the members of your profession and divide the tasks among yourselves - create Git repository for frontend (If you're not the only one working on the project, don't forget to send them an invite to the organization (ff there is one) and add them to the repository's collaborators with “Write” permissions) - add a README.md.md file to the repository describing how to collaborate with the repository. details - connect CodeRabbit AI or CodiumAI PR-Agent service to your organization's GitHub or repository to review Pull Requests - use basic setup of the project (something like React + TypeScript + Vite) - install eslint, prettier, husky (that runs eslint for each commit) - add the main page component and write one line in <h1> - deploy frontend to Netlify (if the repository is in an organization, when importing the repository, select the organization specifically, and you must also have organization owner access) | - get in touch with members of your profession and divide the tasks among yourselves - analyze the references from the requirements. Before making a design, it would not hurt to at least look at the user flow of similar services (references) to understand what kind of design should be on this project, what users are used to, what pages should be included, and what visual style should be used - create a wireframe for the first page | - get in touch with members of your profession and divide the tasks among yourselves - check the project requirements to verify compliance (to ensure that all stated requirements are clear, properly documented, and achievable) and to identify possible gaps (to identify inconsistencies or ambiguities that could lead to errors during the development phase) - set up the environment for the test plan. Also, work with backend developers and prepare Postman or Swagger for API testing - check the requirements for the created tasks in the task tracker whether everything is enough to complete the task - check the completed tasks (if any appear) | - 1:1 with each team member - choose a development methodology (Scrum is suitable for projects with clearly defined requirements and milestones, and Kanban for projects with unpredictable priorities and a constant flow of tasks, responding to changes as they occur) - сhoose a task tracker (Jira or Trello) and create a backlog for all tasks that have not yet been started. Additionally, set up a board with the following columns to reflect the current task status: To Do, Reopen, In Progress, Blocked, Review teammate, Ready for testing, Testing, Done - prepare a board with tasks for 2 weeks. Technical task details (tips on what to look for) for each profession can be added to the corresponding tasks in the task tracker - set up communication between team members - establish dependencies between tasks and encourage participants to communicate and agree on the distribution of tasks - use chats and meetings to discuss common questions and requirements (both for members of a particular profession and for the team as a whole) - schedule regular meetings with the team - set up regular meetings for the members of each profession to meet each other (QA with QA, designer with designer, ...) or with the closest profession (QA with designer, QA with PM, PM with designer) - set up regular meetings at least for such ceremonies of the development methodology as planning and retrospectives - set up a stand-up in your communication channel and monitor its implementation so that each team member writes 3 times a week: what they have done, what they plan to do, what blockers they have - Compare what the person's task was and what they write, because the person may not have understood the task or may have done something different than planned or described the blockers vaguely - make a note to use an icebreaker and small talk when communicating (texting or calling)
Bootstraping | As a user, I want to be able to open a website that speaks to the backend | - open website, dev tools with Network tab and see there request to GET ping with 200 response code - backend can be pinged through Postman | - any endpoints - no database | - backend is deployed - frontend makes a request - backend serves endpoint GET /ping with empty response | Backend: - get in touch with members of your profession and divide the tasks among yourselves - create Git repository for backend (If you're not the only one working on the project, don't forget to send them an invite to the organization (ff there is one) and add them to the repository's collaborators with “Write” permissions) - add a README.md.md file to the repository describing how to collaborate with the repository. details - connect CodeRabbit AI or CodiumAI PR-Agent service to your organization's GitHub or repository to review Pull Requests - use basic setup of the project (according to main documentation of your framework) - Node: TypeScript + Express, Nest, or Fastify - Python: Django - Java: Spring Boot - install linter - Node: eslint, husky (that runs eslint for each commit) - add GET ping endpoint - add cors (depends on the programming language and framework) and list the frontend endpoint for deploy and for local development - deploy backend - Node: Render - connect PostgreSQL using https://neon.tech/ (why SQL instead of noSQL: details) - use database ORM - Node: Drizzle Frontend: - add axios library on frontend - create axios client as singleton in a separate file - import client in your component and make GET request
Bootstraping | As a user, I want to see an error page if I have incorrect link | - open website in /random link and see 404 page | - styling
Bootstraping | As a user, I want to see a toast message if something went wrong (file cannot be downloaded or uploaded etc) | - click on button Toast and see toast | - no real errors, just test button | - if clicked several times, from different components, it should create only one html element in DOM, not several | - install library for toast - create a button that will invoke the toast
Bootstraping | As a user, I want to be able to open a website that gets an image for the logo from the external storage on backend | - GET /public/logo is called on frontend - logo is visible | - no database | - keys are not commited to Git, they are in env variables - backend can download files from S3 | - create S3 storage - upload logo manually there - install aws sdk library - add all security keys to environment variables - create endpoint GET /public/logo, download logo from S3 and return it to the user - use this endpoint on frontend to display logo
Uploading files | As a user, who shares the file, I want to be able to upload the file from my file observer | - open website in main page ('/') and see the form to upload a new file (only image) - the form includes an input field for a file (Browse button that opens a file observer) - another type of file except images cannot be chosen or gives an error - the form includes save button that saves the file to share - when the Save button is clicked and file is saved, the link is shown on frontend and the data can be checked on backend side - when the Save button is clicked and there was an error, the toast message displays error | - styling - being able to download/show file - all types of files (in scope only images) | - make sure you stick to REST, use /api prefix and versioning - files should not create conflicts with filenames | - user chooses the file in the input that is not sent immediately - when save button is clicked, progress bar is shown and all buttons are disabled - meanwhile frontend requests a presigned upload url - frontend uploads the file using a link from S3. details - if the request is successful, the key from the presigned upload url is used to send the full request to saves the entity to backend - if it is successul or not, show a toast and enable buttons, remove progress bar - create endpoint POST /files, that receives the link and stores it in DB as a record of file to be shared and returns an id added to the DB |  | - check the completed tasks (if any appear) |  | -another type of file except images cannot be chosen or gives an error - цей пункт потребує роз'яснення, чому тільки зображення | Тут малося на увазі всі формати, які не підтримуємо, класно відмітили
Downloading files | As a user, who receives the file, I want to see the correct file should be found in the system when I click on the link that was shared with me | - open website on /files/:id to see the file shared (any way to show the file is found) - if there is no file available using this link, show 404 error | - styling - removing the files or checking access - displaying the name of the file - downloading the file |  | - create an endpoint GET /files/:id to return info about file entity
Uploading files | As a user, who shares the file, I want to be able to upload different types of images, documents, pdfs and archives with 50 MB restriction | - open website in main page ('/') and see the form to upload a new file (only image) - the form includes an input field for a file (Browse button that opens a file observer) - the form includes save button that saves the file to share - when the Save button is clicked and file is saved, the data can be checked on backend side - when the Save button is clicked and there was an error, the toast message displays error - the acceptable types of files include: jpg, jpeg, png, gif, doc, docx, xls, xlsx, pdf, zip, rar - if the size of the selected file is more than 50MB, show a validation error and blocks the uploading | - styling - being able to download/show file | - the validation should be on frontend and backend, settings for presigned url |  |  |  |  | if the size of the selected file is more than 50MB, show a validation error and blocks the uploading - чому має блокувати? у нас є пункт що у відправника є можливість компрес. блокування має бути якщо відправник натиснув "ні" компрес, то його має повернути на "Upload the file" | Погоджуюсь, робимо як в user flow
Uploading files | As a user, who shares the file, I want to be able to set a password for the file to restrict the access from public internet | - open website in main page ('/') and see the form to upload a new file (only image) - the form includes an input field for a file (Browse button that opens a file observer) - the form includes a field for password with no minimum requirements (at least 1 symbol) but with max length = 30 symbols - the form includes save button that saves the file to share - when the Save button is clicked and file is saved, the data can be checked on backend side - when the Save button is clicked and there was an error, the toast message displays error - the acceptable types of files include: jpg, jpeg, png, gif, doc, docx, xls, xlsx, pdf, zip, rar - if the size of the selected file is more than 50MB, show a validation error and blocks the uploading - the file with the password cannot be downloaded without password info on download page | - styling - download logic with password - making password an optional field | - escape the password before using it to avoid SQL injections - hash the password before storing it in DB, it shouldn't store explicitly | - add a field on frontend - attach the password to a payload for upload endpoint |  |  |  | the form includes a field for password with no minimum requirements but with max length = 30 symbols - ми домовилися що мінімальна кількість символі - хочаб 1 символ. if the size of the selected file is more than 50MB, show a validation error and blocks the uploading - тут теж є блокування завантаження файлу більше 50 замість запропонування стиснення файлу. якщо користувач не згоден тоді повертає до "Upload the file" | Виправив на 1 символ Погоджуюсь, робимо як в user flow
Uploading files | As a user, who shares the file, I want to share some public files without a password | - being able to share the file with and without password |  |  | - make password field nullable in DB - mark it as optional on frontend
Uploading files | As a user, who shares the file, I want to copy and share the shortened link fast | - display the link to share the file that just has been uploaded - add a copy button for the buffer
Uploading files | As a user, who shares the file, I want to see the error after the storage period to make sure it is not available anymore | - when a file is uploaded, default time to store is 24 hours - the file will be accessible via link during this time to download and show 404 error when it is expired | - changing the time to store file | - make sure you have a configuration setting for the timer as a variable in your code | - set expiration date for the file entity in DB and TTL property (they will point to the same date for now) - configure expiration rule for the bucket. details - files will be removed from DB and S3 after TTL autommatically
Downloading files | As a user, who receives the file, I want to see the name of the file | - the file name is visible on the download page | - downloading the file
Downloading files | As a user, who receives the file, I want to be able to download the file | - open website on /files/:id to see the file shared - a download button is visible - when button is clicked, files start downloading - if there is no file available using this link, show 404 error | - styling - removing the files or checking access - displaying the name of the file | - all links should be presigned by backend to restrict the access for other users later - presigned link should have TTL | - entity from backend includes the S3 bucket presigned link and it is used by frontend to start download
Downloading files | As a user, who receives the file, I want to be able to type the password if needed | - open website on /files/:id to see the file shared - if the file requires a password, it shows a file name, field for password and a Get access button - if password is correct, download button is displayed | - styling | - throttle the requests, so the service cannot be DDOSed - without password verification the presign url shouldn't be sent to frontend
Downloading files | As a user, who receives the file, I want to be able to get the notification if the password is incorrect | - if the password is incorrect, it shows an error
Uploading files | As a user, who shares the file, I want to see a page nice styled | - styles correspond with design (mockup)
Downloading files | As a user, who receives the file, I want to see a page nice styled | - styles correspond with design (mockup)
Uploading files | As a user, who shares the file, I want to see the progress while the files is being uploaded | - the form includes a visible progress bar or percentage indicator that shows the status of the file upload in real-time - the progress indicator is shown after a file is selected and the Save button is clicked - if the file upload is successful, the progress bar reaches 100% and disappears or changes to a "completed" state - if the file upload fails at any point, the progress bar stops and a toast message displays the error - the progress bar should be styled consistently with the rest of the design (based on the mockup)
Uploading files | As a user, who shares the file, I want to be able to upload the file dragging the file into browser window | - the website's main page ('/') includes a drag-and-drop area for file uploads - the drag-and-drop area is visually distinct (e.g., dashed border, drop zone text) to indicate where the user can drop the file - only valid file types (e.g., images, documents, pdfs, archives) can be dragged and dropped - if the user drags an invalid file type into the drop zone, display a validation error and prevent the upload - the acceptable file types include: jpg, jpeg, png, gif, doc, docx, xls, xlsx, pdf, zip, rar - the size of the selected file cannot exceed 50MB. If the file is larger than 50MB, show a validation error and block the upload - once a valid file is dropped, the upload process starts automatically, and the file name appears in the file input field - after the file is successfully uploaded, display the link for sharing on the frontend - if an error occurs during the file upload, a toast message is displayed with an error notification - the drag-and-drop functionality works alongside the existing file upload form (both can be used interchangeably) | [6 empty] | If the file is larger than 50MB, show a validation error and block the upload - тут теж є блокування завантаження файлу більше 50 замість запропонування стиснення файлу. якщо користувач не згоден тоді повертає до "Upload the file" | Хороше підмічання, згідно user flow, там справді має бути пропозція стиснення
Uploading files | As a user, who shares the file, I want to compress files if they larger than the max size while uploading | - the system checks the file size when a user selects a file for upload - if the file is larger than 50 MB (or the specified maximum size), the user is prompted with an option to compress the file - the system provides an automatic compression option for supported file types: images (jpg, jpeg, png, gif), documents (doc, docx, xls, xlsx, pdf), and archives (zip, rar) - once the file is compressed, the user sees a notification that the file has been successfully reduced in size - ffter compression, the compressed file replaces the original file in the upload form - the user can proceed to upload the compressed file without exceeding the 50 MB size limit - if the compression fails for any reason, a toast message is displayed indicating that the file could not be compressed and offering the user the option to either retry or cancel the upload - files that cannot be compressed (e.g., certain non-supported file types) are blocked from uploading with an appropriate validation message explaining that compression is not available for these files - once compression is complete, a message is shown indicating the new file size and confirming that the file is ready for upload
Uploading files MVP | As a user, who shares the file, I want to be able to zip or rar file if I upload the folder | - open website on the main page ('/') and see the form to upload a new file or folder - the form includes an input field for selecting a folder (Browse button that opens the file observer) - when a folder is selected, the system automatically zips or rars the folder before uploading - the form includes a save button that saves the zipped or rared folder to share - when the Save button is clicked and the file is saved, the link to the zipped or rared folder is shown on the frontend and the data can be checked on the backend side - when the Save button is clicked and there was an error (e.g., file too large or unsupported format), a toast message displays the error - the acceptable compressed formats are .zip and .rar - if the size of the zipped or rared file is more than 50MB, show a validation error and block the upload | [6 empty] | - тут мається на увазі заархівувати папку якщо вона більша за 50МВ?(30.09.2024 р.) -when a folder is selected, the system automatically zips or rars the folder before uploading- ту має бути вибір між zip та rar(цього немає в юзер флоу, але як система буде обирати у який формат стискати?) без автоматичного стиснення і згідно юзер флоу тут має повертати до "Upload the file" замість блокування(06.10.2024) | -Так, папки більше 50МВ. Тут мається на увазі архівація будь-якої папки. (01.10.2024р.) | 1.Не уточнено, чи користувач може вибирати між .zip та .rar, або система автоматично вирішує це.2.Вказується, що можна завантажувати як файли, так і папки, але не деталізовано, що відбувається при виборі окремого файлу (чи він не стискається?).- the form includes an input field for selecting a folder (Browse button that opens the file observer) - пункт 10 сказано, що таким чином можна обрати тільки файли зображення, а в пункті 26 вже і папку.(06.10.2024) | 1. Давайте зробимо zip автоматично (бо в user flow поки немає вибору розширення) 2. Давайте файли також стискати знідно user flow (07.10.2024)
Downloading files v2.0 | As a user, who receives the file, I want to be able to convert the image or archive type while downloading | - when a user opens the download page (/files/:id), a conversion option is displayed for images and archives before downloading - for images, the supported conversion types are: jpg, png, gif, and webp - for archives, the supported conversion types are: zip and rar - a dropdown or select field allows the user to choose the desired file format (based on the original type) before starting the download - when the user selects a different format and clicks the download button, the backend handles the file conversion and provides the converted file for download - if the selected file format is the same as the original, the file is downloaded without conversion - if the conversion fails, the system shows a toast message indicating the error, and the original file remains available for download - the converted file size must remain within the 50MB limit. If the conversion results in a file larger than 50MB, an error message is displayed, and the download is blocked - if the file requires a password, the user must first enter the correct password before the conversion and download options become available | [6 empty] | Треба забрати з User Flow
Downloading files v2.0 | As a user, who receives the file, I want to see the picture or pdf file if they can be displayed by a browser | [7 empty] | це проговорювалося для першої версії | Для 1 версії залишається без прев'ю, достатньо назви файлів
Uploading files v2.0 | As a user, who shares the file, I want to be able to convert the image or archive type while uploading | [7 empty] | це прописано в user flow для першої версії | Тільки для скачування для 1 версії
Uploading files v2.0 | As a user, who shares the file, I want to set time period how long the file is stored in the storage | - on the upload page user can pick how long this file will be stored - if nothing is chosen, default value is 1 day - the max period is 30 days - the file is not visible on website and cannot be downloaded after set period of time |  |  | - change TTL in DB and lifecycle configuration in S3 bucket to the mmax period as per period options - set expiration date from user to entity in DB - if user tried to load page with object that exists in DB, check if it is expired, and if yes, return 404 and remove objects from DB and S3 |  |  |  | для першої версії ми обговорювали можливість за замовчуванням 24 години максимум 2 тижні | Для 1 версії 24 год лишаємо без можливості змінювати період
Uploading files v2.0 | As a user, who shares the file, I want to have time period how long the file is stored in the storage set by default to 2 weeks (this is max) when I don't want to pick it | [7 empty] | для першої версії ми обговорювали можливість за замовчуванням 24 години максимум 2 тижні | Для 1 версії 24 год лишаємо без можливості змінювати період
Uploading files v2.0 | As a user, who shares the file, I want to be able to upload file that can be downloaded just once and removed after immediately
Downloading files v2.0 | As a user, who receives the file, I want to see the content if the file is an archive
Downloading files v2.0 | As a user, who receives the file, I want to download only selected file from the archive
Uploading files v2.0 | As a user who shares a file, I want to have restrictions on the minimum password length as well as the symbols allowed | [7 empty] | для першої версії ми обговорювали мінімальний пароль в 1 символ | Для 1 версії лишається 1 символ
Uploading files v2.0 | As a user, who shares the file, I want to be able to upload videos

## Requirements
Category | Requirement | Questions | Comments | Version
Links | Tiny links should be unique, no duplicates, the same size (100 symbols) | як можна буде перевірити унікальність?(скільки разів треба буде сформувати посилання , щоб ми могли точно сказати що воно унікальне) | 5
Links | Tiny links should be random, not predictable. Use hashing | як можна буде перевірити рандомність?(скільки разів треба буде сформувати посилання , щоб ми могли точно сказати що воно рандомне) | 5
Links | No restrictions on filename and different users can load files with the same name
Passwords | Passwords cannot be stored as text. Use hashing
Passwords | No restrictions for symbols (any symbols are suitable)
Passwords | No minimum requirements (at least 1 symbol) but with max length = 30 symbols
Files | Files should be invisible immediately after the expiration |  | 24 годин
Files | Files should be cleaned up periodically | який саме період? | для MVP 24 год
Files | You need to avoid out of memory having the restriction of 500 MB storage for all files | сумарно для всіх? | Для всіх файлів 500 MB
Files | Files should be checked by the extensions. Only popular safe extensions can be loaded. | популярні це які саме? Прописати весь перелік графічний, документів, архіви, відео, аудіо, інші. Інформування користувача? | jpg, jpeg, png, gif, doc, docx, xls, xlsx, pdf, zip, rar
Files | Files should have max size of 50 MB |  | для відправника- перед завантаженням(або стискання), для отримувача- перед завантаженням після конвертації
Files | Folders and files should have the ability to be compressed. | я думаю, що тут не вистачає про можливість стискання файлів зі сторони відправника , якщо файл більше 50 МБ або папка | Погоджуюсь, бо це є в User Flow
Conversion | Supported conversion: between images, image to pdf and back, rar to zip and back |  | тільки для отримувача | v2.0
Conversion | Conversion is asynchronous and should be handled on frontend, polling for the status of the conversion and load when ready
Conversion | User should be informed about progress of any long processes | як саме буде виглядати? | прогрес бар з відсотками
Conversion | UI should handle failed downloads |  | буде повідомлення про невдалу спробу
Components | Drag and drop should be a custom component
Components | Toast message should be a custom component and a singleton
Quality | Unit tests coverage up to 70% for frontend and backend
Quality | Integration tests coverage with one full happy path
Quality | Storybook should include custom components